|  |
| --- |
| MSDIWG5 - 11 |

**5th Marine Spatial Data Infrastructure Working Group Meeting**

**(MSDIWG)**

**Silver Spring, Maryland, United States, February, 5-7, 2014**

**Summary of MSDIWG Actions**

|  |  |  |  |
| --- | --- | --- | --- |
| **Subject** | **ACTION**  **No.** | **ACTIONS**  **(in bold, action by)** | **Status**  **7 February, 2014** |
|  | 1 | **Private companies** (ESRI and OceanWise) to prepare a paper on MSDI challenges and how to cope with them; Submit to MSDIWG-6 | Complete |
|  | 2 | **AU (M McGregor)** to present a first draft of information/data provider and user audit to MSDIWG-6 | Secretary to draft a letter. |
|  | 3 | **AU, DK, JP and US** to present a list of relevant initiatives to MSDIWG-6 | Done. RHC to put it in the reports to IRCC |
|  | 4 | **AU, DK and SP** to present a paper to MSDIWG- 6 proposing which initiatives the MSDIWG should be engaged in and if deemed appropriate to suggest a test case or a project to illustrate the challenges and benefits | Not started |
|  | 5 | **DK to** present a paper to HSSC6 about the impact of the UN-GGIM initiative, taking into account the items identified in paragraph 11 of HSSC5-05.7B, | Completed. |
|  | 6 | **AU and DK** to present a paper to MSDIWG-6 presenting relevant use cases, content of use cases and benefits | Not started. New item on coordination with GSDI |
|  | 7 | **AU (M McGregor)** to prepare a paper to MSDIWG-6 about the international registry of maritime boundaries | Not started |
|  | 8 | **Chair (JPH)** WG Chair to write to all WG Members asking for them to confirm their willingness to remain on the MSDIWG. It is important that tall members all contribute to the Work Plan, Conferences and Task Groups | Completed |
|  | 9 | Chair (JPH). WG Chair to re-submit a request for IHO funding to support outreach for MSDIWG for 2014-18 | Not started |
|  | 10 | **UK,JP,US and Esri** to submit position paper to IRCC on value and benefit of MSDI to HO’s and the role of RHC’s supporting this | Completed |
|  | 11 | **UK** to send out to NO, NL, Caris and Envitia a proposed setup to identify requirements on additional S-1xx data specifications, to prepare preliminary feedback to HSSC6 (B.1.1) NO, NL, Caris and Envitia to comment on proposal. | Completed |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |