## S-101 Proposals
Colour Key
| PINK | Not yet incorporated or need a revised proposal
| BLUE | Monaco DCEG Actions for proposals
Proposal Name | Proposal Type | General Notes | Assigned | FDD | DCEG | DCEG approved | Included in FC | Convertor Need | Convertor Complete | Portrayal Need | Portrayal Complete | Included in PC | Proposal
Quality of Bathymetric Data | Feature | This proposal replaces M_QUAL |  |  | Y |  |  | Y |  | Y |  |  | DQWG Proposal
Quality of Survey | Feature | This proposal replaces M_SREL |  |  | Y |  |  | Y |  | Y |  |  | DQWG Proposal
Quality of Nonbathymetric Data | Feature | This proposal replaces M_HOPA |  |  | Y |  |  | Y |  | Y |  |  | DQWG Proposal
Nautical Publication Information (M_NPUB) | Portrayal Only |  | - | - | - | - | - | - | - | Y
Data Coverage (M_COVR) | Feature | This proposal has been accepted by TSMAD | TR |  | Y | Y |  | Y |  | Y |  |  | Data Coverage Proposal
M_SDAT/VERDAT | Portrayal Only | Need to provide an indication to the mariner for when they are moving from one sounding datum to another | - | - | - | - | - | - | - | Y |  |  | N/A
Control Point |  | Control Point has been removed from S-101. The convertor should map to LNDMRK | - | - | - | - | - | Y | - | - | - | -
LOCMAG |  |  | - | - | - | - | - | - | - | - | - | -
Value of Local Magnetic Anomoly | Complex Attribute | This is a new attribute to replace LOCMAG as a complex. Convertor should map VALMMA to valueMaximum of the Complex | TR |  | Y | Y |  | Y
valueMinimum | Simple Attribute | part of the Local Magnetic Complex, should be used by other features that require a min and max value | TR |  | Y | Y |  | Y
valueMaximum | Simple Attribute | part of the Local Magnetic Complex, should be used by other features that require a min and max value | TR |  | Y | Y |  | Y
Additional Ice features from the ICE FDD | Multi |  | - | [9 empty] | Need to do further research as to which features are most appropriate for inclusion
Span | Feature |  | TR |  | Y | Y |  | Y |  | Y
Vertical Clearance | Complex Attribute |  | TR |  | Y
Clearance value | Simple Attribute |  |  |  | Y
Vertical Clearance Type | Simple Attribute |  | TR |  | Y
Vertical Closed | Ennumerant |  |  |  | Y
Vertical open | Ennumerant |  | TR |  | Y
Vertical fixed | Ennumerant |  | TR |  | Y
safe | Ennumerant |  | TR |  | Y
Clearance accuracy | Simple Attribute | VERACC is now Vertical Uncertainty |  |  | Y
Horizontal clearance | Complex Attribute |  |  |  | Y
Clearance value | Simple Attribute |  |  |  | Y
Horizontal Clearance Type | Simple Attribute |  |  |  | Y
Horizontal open | Ennumerant |  | TR |  | Y
Horizontal closed | Ennumerant |  | TR |  | Y
Horizontal Fixed | Ennumerant |  | TR |  | Y
Clearance accuracy | Simple Attribute | HORACC is now Horizonatal Distance Uncertainty |  |  | Y
Category of span | Simple Attribute |  | TR |  | Y
Fixed | Ennumerant |  | TR |  | Y
Opening | Ennumerant |  | TR |  | Y
Consists of | Association | See revised UKHO proposal and model | TR | [9 empty] | Bridges Proposal v.2
Structure | Association | See revised UKHO proposal and model | TR | [9 empty] | Bridges Proposal v.3
Component | Association | See revised UKHO proposal and model | TR | [9 empty] | Bridges Proposal v.4
Feature Name (OBJNAM) | Complex Attribute | Refined at DCEG Monaco 2012 |  |  | Y | Y |  | Y
Display Name | Simple Attribute | Boolean for which name should be on the ECDIS display |  |  | Y | Y |  | Y
Language | Simple Attribute |  |  |  | y | Y |  | Y
Name | Simple Attribute |  |  |  | Y | Y |  | Y
Information | Complex Attribute |  |  |  | Y | Y |  | Y
Language | Simple Attribute |  |  |  | Y | Y |  | Y
Text | Simple Attribute |  |  |  | Y | Y |  | Y
Textual Description (TXTDSC) | Complex Attribute |  |  |  | Y | Y |  | Y
File reference | Simple Attribute |  |  |  | Y | Y |  | Y
Language | Simple Attribute |  |  |  | Y | Y |  | Y
CTNARE - bindings |  | Add CONDTN and STATUS as bindings | - | - | - | - | - | - | - | - | - | -
condition | New Binding |  |  |  | Y | Y | - | - | - | - | - | -
Status | New Binding |  |  |  | Y | Y | - | - | - | - | - | -
Checkpoint | Portrayal Only | Need to add portrayal of the point primitive | - | - | - | - | - | - | - | Y
Pile Point | Portrayal Only | Need to add display for Point and line | - | - | - | - | - | - | - | Y | - | -
Category of Pile |  |  | - | - | - | - | - | - | - | - | - | -
Piling | Ennumerant |  | EM |  | Y | Y
area of piles | Ennumerant |  | EM |  | Y | Y
Pipe | Ennumerant |  | EM |  | Y | Y
DYKCON |  | Add CONVIS as a binding | - | - | - | - | - | - | - | - | - | -
Convis | New Binding |  |  |  | Y | Y
Distance Mark |  |  | - | - | - | - | - | - | - | - | - | -
Measured Distance Value | Complex Attribute |  | TR |  | Y | Y | [6 empty] | Distance Mark Proposal
Distance of Unit measurement | Simple Attribute |  | TR |  | Y | Y
Kilometres | Ennumerant |  | TR |  | Y | Y
Statute mile | Ennumerant |  | TR |  | Y | Y
Nautical mile | Ennumerant |  | TR |  | Y | Y
Sea mile | Ennumerant |  | TR |  | Y | Y
yards | Ennumerant |  |  |  | Y | Y
Referenced Location | Simple Attribute |  | TR |  | Y | Y
Waterway Distance | Simple Attribute |  | TR |  | Y | Y
DAMCON |  | add WATLEV | - | - | - | - | - | - | - | - | - | -
WATLEV | New Binding
BERTHS | New Binding | Bind LG_DRT (maximum permitted draft), HORCCL, HORCLW from the IEHG register | - | - | - | - | - | - | - | - | - | -
Maximum permitted draft | New Binding |  |  |  | Y | Y |  |  |  | Y
Horizontal Clearance Width | New Binding
Horizontal Clearance Length | New Binding
DRYDOC | New Binding | Bind LG_DRT (maximum permitted draft), HORCCL, HORCLW from the IEHG register | - | - | - | - | - | - | - | - | - | -
Maximum permitted draft | New Binding |  |  |  | Y | Y
Horizontal Clearance Width | New Binding
Horizontal Clearance Length | New Binding
FLODOC | New Binding | Bind LG_DRT (maximum permitted draft), HORCCL, HORCLW from the IEHG register | - | - | - | - | - | - | - | - | - | -
Maximum permitted draft | New Binding |  |  |  | Y | Y
Horizontal Clearance Width | New Binding
Horizontal Clearance Length | New Binding
MORFAC |  |  | - | - | - | - | - | - | - | - | - | -
CATSCF | New Binding | Restricted to 8: visitor mooring
Named Association | Association | To do | TR | [9 empty] | Need to develop a named association/Aggregation
DOCARE | Portrayal Only | fix it on the portrayal side to display differently if it is on navigable versus navigable water. Also applicable to other features - RIVERS, LAKES | - | - | - | - | - | - | - | Y
LOKBSN | Portrayal Only | fix it on the portrayal side to display differently if it is on navigable versus navigable water. Also applicable to other features - RIVERS, LAKES | - | - | - | - | - | - | - | Y
Information Area | Feature | Still needs to get the kinks worked out. Could we handle this with a boolean on the CTNARE of alarm/no alarm. UKHO to propose with France | TR | [9 empty] | DCEG.17 Information Area
COLREGS | Feature |  | JLP | [9 empty] | DCEG.17 COLREGS
TS_PAD - General Tides | Multi | Tidal Stream Panel Data Proposal | TR |  | Y | Y |  |  |  | Y |  |  | UKHO Proposal accepted
CURRENT | Portrayal Only |  | - | - | - | - | - | - | - | Y |  |  | Added Area and Line as new primitives. Need encoding and portryal
CURRENT |  | Agree to complex use the new simple attributes for valueMininum and valueMaximum. Need to write the proposal. Add the mean value | TR | - | - | - | - | - | - | - | - | -
Current Velocity | Complex Attribute |  |  |  | Y | Y
Velocity Maximum |  |  |  |  | Y | Y
Velocity Minimum |  |  |  |  | Y | Y
HULKES |  | Add new ennumerant training vessel | JLP | - | - | - | - | - | - | - | - | -
CATHLK |  |  |  | - | - | - | - | - | - | - | - | -
7: training vessel | Ennumerant |  |  |  | Y | Y
OSPARE | Simple Attribute |  | - | [9 empty] | Defined limits OSPARE add attribute to support display of limits or not. Solution for groups of islands also needed.
No Bottom Found | Feature | no bottom found.doc | AT |  | Y | Y | [6 empty] | New feature for no bottom found
DRGARE |  |  | JLP | - | - | - | - | - | - | - | - | - | Add new attribute for dredge date
Dredged Date | Simple Attribute | Dredge Date Proposal |  |  | Y | Y
DRGARE - display | Portrayal Only |  | - | - | - | - | - | - | - | Y |  |  | Need to come up with protryal of the depth in DRGARE
SWPARE |  |  | - | - | - | - | - | - | - | - | - | - | Add new attribute for swept date
Swept Date | Simple Attribute | Swept Date Proposal |  |  | Y | Y
UNSARE | Portrayal Only |  | - | - | - | - | - | - | - | Y |  |  | If there is data encoded with UNSARE such as depths the portryal is obscurred by the UNSARE itself
Surface Quality | Complex Attribute | Added to all features that use NATSUR/NATQUA |  |  | Y | Y |  | Y
Nature of Surface | Simple Attribute |  | TR |  | Y | Y |  | Y
Nature of Surface - Qualifying terms | Simple Attribute |  |  |  | Y | Y |  | Y
Surface layer | Simple Attribute |  | TR |  | Y | Y |  | Y
WRECKS | Portrayal Only |  | - | - | - | - | - | - | - | Y |  |  | issues with a isolated danger showing because there is no VALSOU and it is a non-dangerous wreck
OBSTRN |  |  | - | - | - | - | - | - | - | - | - | -
Category of Obstruction |  |  | - | - | - | - | - | - | - | - | - | -
Manifold Wave Energy Device | Ennumerant |  |  |  | Y | Y
Fish Aggregating Device | Ennumerant |  |  |  | Y | Y | [6 empty] | Multiple suggestions that this is either CATOBS or CATFIF
Artifical Reef | Ennumerant |  |  |  | Y | Y
OBSTRN | Portrayal Only |  | - | - | - | - | - | - | - | Y |  |  | Display centred isodgr symbol? And priority rocks etc may display over.
Foul Ground | Feature | Foul Ground Proposal.doc | TR |  | Y | Y |  |  |  | Y
FSHFAC | Portrayal Only |  | - | - | - | - | - | - | - | Y |  |  | display and alarm functionality for FSHFACS needs to be addressed in the PC/PS
FSHFAC |  |  | - | - | - | - | - | - | - | - | - | - | Bind VALSOU
VALSOU | New Binding
Wave Energy Devices | Multi | To do | TR | [9 empty] | Need to look at this as a whole and not in parts (Richard Fowele) - see OBSTRN
Wind Turbine | Feature | wind turbine.doc | AT | [9 empty] | Need a worked up proposal for Wind Turbine
CATPRA |  | These are all under OBSTRN. Not sure if we agreed. | TR | [9 empty] | Add offshore flare stack
Offshore Flare Stack | Ennumerant
wave energy devies | Ennumerant |  | TR | [9 empty] | Add wave energy devices
underwater turbines | Ennumerant |  | TR | [9 empty] | add underwater turbines
Seabed material extraction area | Ennumerant | [11 empty] | Instead of RESARE, the feature OSPARE should be used in this situation, as it can describe the restrictions (RESTRN), the extracted material (PRODTC) and possibly the facilites (CONVIS, HEIGHT, VERLEN...). An enumerated value is missing for CATPRA to complete the description. So, I propose to create a new one "CATPRA = Seabed material extraction area" (see proposal in annex). This new value will be sufficient to warn the mariners about the possible presence of dredging facilities in the area.
Traffic Separation Schemes | Association | [11 empty] | Need to determine if it is useful for the mariner
RCRTCL | Portrayal Only |  | - | - | - | - | - | - | - | Y |  |  | is there anyway to not have to use direction of digitizing, but the orient value
DWRTCL | Portrayal Only |  | - | - | - | - | - | - | - | Y |  |  | is there anyway to not have to use direction of digitizing, but the orient value
DateRange | Complex Attribute | Date Range Proposal | JLP |  | Y | Y |  | Y |  |  |  |  | See French Proposal as a basis
ARCSLN | Association | [11 empty] | Need to determine if it is useful for the mariner
VTS area feature | Feature | VTS Area Proposal.doc | TR |  | Y | Y | [6 empty] | Use the IEHG feature for this
RDOCAL - line | Feature | [11 empty] | Jeppesen to propose a RDOCAL line proposal, separate the point and line into two feature which may resolve mandatory versus conditional values for points and lines
CATFRY |  |  | - | - | - | - | - | - | - | - | - | -
5: High Speed Ferry | Ennumerant | ADD: 5: High Speed Ferry | JLP |  | Y | Y | [6 empty] | New ennumerant for High Speed Ferry. Needs to be number 5 because IEHG has 4 reserved
COMCHA | Complex Attribute | [11 empty] | DCEG.25 Communication Informaiton
Maritime Jusisdiction Areas | Multi | [11 empty] | France and Australia will re-submit the 200? Proposal from years ago
ACHARE | Portrayal Only |  | - | - | - | - | - | - | - | Y |  |  | Name for the ACHARE needs to be displayed In order to avoid the display of the crossed anchor (as a result of the encoding of RESTRN=2 and the CSP RESTRN01), I propose to prohibit the use of RESTRN = 2 for ACHARE feature and to create a new enumerated value "CATACH = Special purpose anchorage area"
Category of Anchorage |  | ADD: 14: waiting anchorage | JLP | - | - | - | - | - | - | - | - | - | Add waiting anchorage, make number 14 as IEHG has the others reserved
14: Waiting Anchorage | Ennumerant |  |  |  | Y | Y
ACHBRT | Portrayal Only |  | - | - | - | - | - | - | - | Y |  |  | Either add a new display rule in the S101 portrayal catalogue to display an area anchor berth encoded by the centre point and the attribute RADIUS, or impose (in the DCEG) the encoder to digitise the true limit of the anchor berth.
MIPARE |  |  | - | - | - | - | - | - | - | - | - | -
Nation | New Binding |  |  |  | Y | Y | [6 empty] | Add NATION as a binding
SUBTLN |  |  | - | - | - | - | - | - | - | - | - | -
Nation | New Binding |  |  |  | Y | Y
Orient | New Binding |  | -
Trafic | New Binding |  | -
ADMARE | Portrayal Only |  | - | - | - | - | - | - | - | Y |  |  | add a new display rule in the S101 portrayal catalogue to display OBJNAM of ADMARE.
CTSARE |  |  | - | - | - | - | - | - | - | - | - | -
RESTRN | New Binding
TESARE/CONZNE/EEZARE |  |  | - | - | - | - | - | - | - | - | - | - | Bind Status
Status | New Binding |  | ? | [9 empty] | Add new ennumerant = in dispute
In Dispute | Ennumerant
CATSPM |  |  | - | - | - | - | - | - | - | - | - | - | Create new enumerate values CATSPM = 29 (Nature reserve mark) and CATSPM = 30 (Fish aggregating device mark) Need to use 58 and 59 as IEHG has the others reserved
58: Nature Reserve Mark | Ennumerant
59: Fish Aggregating Device Mark | Ennumerant
PILPNT/PYLONS/FORSTC/CURRENT
Status | New Binding
STATUS |  |  | ?
working unreliable | Ennumerant
CATHAF |  |  | - | - | - | - | - | - | - | - | - | - | Add new ennumerant pilotage service (use number 18, IEHG has the others reserved) DCEG needs to be 18 not 15
18: Pilotage service | Ennumerant
Synchro Lift | Ennumerant | Monaco Action | GU
FSHFAC |  |  | - | - | - | - | - | - | - | - | - | - | add CONDTN
CONDTN | New Binding |  |  |  | Y | Y
CONRAD |  |  | ? | - | - | - | - | - | - | - | - | -
ALL FEATURES | New Binding | add CONRAD to all features. Restrict to value 3 for line primitives.
TOPMAR | Complex Attribute | Topmark Proposal.doc | TR |  | Y | Y | [6 empty] | Agreed to create a complex attribute for TOPMAR and investigate the other equipment objects for making possible complex attributes
COLOUR and COLPAT | Complex Attribute |  | - |  | Y | Y | [6 empty] | Need to get mariner feedback as to wether colour pattern is useful - part of topmark complex
Pilotage District Feature | Feature | Pilot District Feature Proposal.doc | TR |  | Y | Y | [6 empty] | would be used with COMCHA - UKHO to propose
CATCRN |  |  |  | - | - | - | - | - | - | - | - | - | Add new ennumerant construction crane
Construction Crane | Ennumerant |  | JW
CATLMK | Portrayal Only |  | - | - | - | - | - | - | - | Y |  |  | Not all values for CATLMK have their own symbol, some just have the default symbol for LNDMRK
OFSPLF | Portrayal Only |  | - | - | - | - | - | - | - | Y |  |  | Seem to be the same symbol for OFSPLF regardless of value for CATOFP
CATROS | Ennumerant |  |  |  | Y | Y
15: Radio Telepone Station
CATREA |  |  | JW | - | - | - | - | - | - | - | - | - | add new ennumerant for port security area
port security area | Ennumerant |  |  |  | Y | Y
CATROD |  |  |  | - | - | - | - | - | - | - | - | - | add new ennumerant for crossing
crossing | Ennumerant
depthRangeMinimum | Simple Attribute |  |  |  | Y |  |  | Y |  |  |  |  | DRVAL1 becomes depthRangeMinimum
depthRangeMaximum | Simple Attribute |  |  |  | Y |  |  | Y |  |  |  |  | DRVAL2 becomes depthRangeMaximum
Update information | Feature | Update Information Proposal.doc | TR |  | Y | [7 empty] | new feature for update information
Update description | Simple Attribute | Update Information Proposal.doc | TR |  | Y | [7 empty] | new feature for update information
Update source | Simple Attribute | Update Information Proposal.doc | TR | [9 empty] | new feature for update information
Update reference | Simple Attribute | Update Information Proposal.doc | TR |  | Y | [7 empty] | new feature for update information
Updated information | Association | Update Information Proposal.doc | TR |  | Y | [7 empty] | new feature for update information
Updates | Association | Update Information Proposal.doc | TR | [9 empty] | new feature for update information
Updated by | Association | Update Information Proposal.doc | TR | [9 empty] | new feature for update information
Reported Date | Simple Attribute | Bind to: Sounding, Underwater Rock, Wrecks, Obstruction, Foul Ground, Pingos, Local Magnetic Anomaly, Caution Area | [10 empty] | DCEG.4_Reported Date
Periodic Complex | Complex Attribute |  |  |  | Y | Y |  | Y
Fixed Complex | Complex Attribute |  |  |  | Y | Y |  | Y
Survey Date Range | Complex Attribute |  |  |  | Y | Y |  | Y
Radar Transponder Beacon
Radar Wavelength | Complex Attribute | [11 empty] | DCEG.8 Radar Wavelength
Value of wavelength | Simple Attribute
Wave Band | Simple Attribute
Sector | New Binding | Add Sector Complex attribute
Depth Discontinuity | Feature | [11 empty] | DCEG.18 Depth Discontinuity
Light List Number | Complex Attribute | Bind to Relevant Aids to Navigation | JLP
Discoloured Water | Feature | [11 empty] | DCEG.18 Discoloured Water

## Data
Feature
Simple Attribute
Ennumerant
Complex Attribute
Information Type
Association
Multi
Portrayal Only
New Binding
Role