## Slide 1
Member States Approve S-101
Update S-57 to S-101 Convertor
Finalize S-101
User Review and Input
OEMs Implement S-100 based ECDIS
ECDIS On-Shore Trials
Converted S-57 or Full S-101 ENC Data Available
S-101 Test Bed Development and Iterative Testing
ECDIS Sea Trials
OEMs Develop S-100 ECDIS
ENC Production Systems
HSSC Approves S-101
S-101 Draft Version
Draft S-58 & S-64 for S-101 Available
Finalize Portrayal Section of S-101
Finalize Draft of S-101 for Testbed
Update S-57 to S-101 Convertor and Make Sample S-101 Data Available for Review
Sample S-101 Data made Available
Retire S-57 and S-52
Final S-101 Stakeholder Review
OEMs
S-101 PT
HOs
Stakeholders
S-100 WG
Responsible Party
S-101 Development and S-100 Testbed Timeline
Revised
Draft S-58 & S-64 for S-101
Release S-101 for Operational Use
S-101 Test Bed Development and Iterative Testing
Draft S-58 and S-64 for S-101
User Review and Input
FEB
MAR
APR
MAY
JUN
JULY
AUG
SEP
OCT
NOV
DEC
JAN
+2 (2015)
+3
+2
+3
+4
+5
+7
+6
Year 1
…
Prepare Test Data – Feature and Portrayal Catalogues and test datasets
2nd Iteration S-57 to S-101 convertor
S-101 Test Version
Portrayal Catalogue Builder Update
S-100 Simple Viewer
S-101 Portrayal Catalogue

## Slide 2
Member States Approve S-101
Update S-57 to S-101 Convertor
Finalize S-101
User Review and Input
OEMs Implement S-100 based ECDIS
ECDIS On-Shore Trials
Converted S-57 or Full S-101 ENC Data Available
S-101 Test Bed Development and Iterative Testing
ECDIS Sea Trials
OEMs Develop S-100 ECDIS
ENC Production Systems
HSSC Approves S-101
S-101 Draft Version
Draft S-58 & S-64 for S-101 Available
Complete Portrayal Section of S-100
Finalize Portrayal Section of S-101
Finalize Draft of S-101 for Testbed
Update S-57 to S-101 Convertor and Make Sample S-101 Data Available for Review
Sample S-101 Data made Available
Retire S-57 and S-52
Final S-101 Stakeholder Review
OEMs
TSMAD
HOs
Stakeholders
DIPWG
Responsible Party
S-101 Development and S-100 Testbed Timeline
January 1, 2015 Progress
Draft S-58 & S-64 for S-101
Release S-101 for Operational Use
S-101 Test Bed Development and Iterative Testing
Draft S-58 and S-64 for S-101
User Review and Input
FEB
MAR
APR
MAY
JUN
JULY
AUG
SEP
OCT
NOV
DEC
JAN
+1 (2014)
+2
+2
+3
+4
+5
+7
+6
Year 1
…
Prepare Test Data – Feature and Portrayal Catalogues and test datasets
2nd Iteration S-57 to S-101 convertor
S-101 Test Version
S-100/S-101 Test Cases Drafted
Portrayal Catalogue Builder
Feature Catalogue BuilderPrototype
S-101 Simple Viewer
DELAYED
DELAYED
COMPLETED

## Slide 3
Member States Approve S-101
Update S-57 to S-101 Convertor
Finalize S-101
User Review and Input
OEMs Implement S-100 based ECDIS
ECDIS On-Shore Trials
Converted S-57 or Full S-101 ENC Data Available
S-101 Test Bed Development and Iterative Testing
ECDIS Sea Trials
OEMs Develop S-100 ECDIS
ENC Production Systems
HSSC Approves S-101
S-101 Draft Version
Draft S-58 & S-64 for S-101 Available
Complete Portrayal Section of S-100
Finalize Portrayal Section of S-101
Finalize Draft of S-101 for Testbed
Update S-57 to S-101 Convertor and Make Sample S-101 Data Available for Review
Sample S-101 Data made Available
Retire S-57 and S-52
Final S-101 Stakeholder Review
OEMs
TSMAD
HOs
Stakeholders
DIPWG
Responsible Party
S-101 Development and S-100 Testbed Timeline
Draft S-58 & S-64 for S-101
Release S-101 for Operational Use
S-101 Test Bed Development and Iterative Testing
Draft S-58 and S-64 for S-101
User Review and Input
FEB
MAR
APR
MAY
JUN
JULY
AUG
SEP
OCT
NOV
DEC
JAN
+1
+2
+2
+3
+4
+5
+7
+6
Year 1
…
Prepare Test Data – Feature and Portrayal Catalogues and test datasets
2nd Iteration S-57 to S-101 convertor
S-101 Test Version
S-100/S-101 Test Cases Drafted
Portrayal Catalogue Builder
Feature Catalogue Builder Prototype
S-101 Simple Viewer

## Slide 4
Member States Approve S-101
Update S-57 to S-101 Convertor
Finalize S-101
User Review and Input
OEMs Implement S-100 based ECDIS
ECDIS On-Shore Trials
Converted S-57 or Full S-101 ENC Data Available
S-101 Test Bed Development and Iterative Testing
ECDIS Sea Trials
OEMs Develop S-100 ECDIS
ENC Production Systems
HSSC Approves S-101
S-101 Draft Version
Draft S-58 & S-64 for S-101 Available
Complete Portrayal Section of S-100
Finalize Portrayal Section of S-101
Finalize Draft of S-101 for Testbed
Update S-57 to S-101 Convertor and Make Sample S-101 Data Available for Review
Sample S-101 Data made Available
Retire S-57 and S-52
Final S-101 Stakeholder Review
OEMs
TSMAD
HOs
Stakeholders
DIPWG
Responsible Party
S-101 Development and S-100 Testbed Timeline
Draft S-58 & S-64 for S-101
Release S-101 for Operational Use
S-101 Test Bed Development and Iterative Testing
Draft S-58 and S-64 for S-101
User Review and Input
FEB
MAR
APR
MAY
JUN
JULY
AUG
SEP
OCT
NOV
DEC
JAN
2014
2015
2014
2015
2016
2017
2019
2018
2013
…
Prepare Test Data – Feature and Portrayal Catalogues and test datasets
2nd Iteration S-57 to S-101 convertor
S-101 Test Version
S-100/S-101 Test Cases Drafted
Portrayal Catalogue Builder
Feature Catalogue Builder Prototype
S-101 Simple Viewer

## Slide 5
Member States Approve S-101
Update S-57 to S-101 Convertor
Finalize S-101
User Review and Input
OEMs Implement S-100 based ECDIS
ECDIS On-Shore Trials
Converted S-57 or Full S-101 ENC Data Available
S-101 Test Bed Development and Iterative Testing
ECDIS Sea Trials
OEMs Develop S-100 ECDIS
HSSC Approves S-101
S-101 Draft Version
IEC 61174 PAS made available
Draft S-58 & S-64 for S-101 Available
Complete Portrayal Section of S-100
Finalize Portrayal Section of S-101
Finalize Draft of S-101 for Testbed
Update S-57 to S-101 Convertor and Make Sample S-101 Data Available for Review
Sample S-101 Data made Available
Retire S-57 and S-52
Final S-101 Stakeholder Review
OEMs
TSMAD
HOs
Stakeholders
DIPWG
Responsible Party
S-101 Development and S-100 Testbed Timeline
Draft S-58 & S-64 for S-101
Release S-101 for Operational Use
S-101 Test Bed Development and Iterative Testing
Draft S-58 and S-64 for S-101
User Review and Input
FEB
MAR
APR
MAY
JUN
JULY
AUG
SEP
OCT
NOV
DEC
JAN
2014
2015
2014
2015
2016
2017
2019
2018
2013
…
Prepare Test Data – Feature and Portrayal Catalogues and test datasets
2nd Iteration S-57 to S-101 convertor
S-101 Test Version
S-100/S-101 Test Cases Drafted
Portrayal Catalogue Builder
Feature Catalogue Builder Prototype
S-101 Simple Viewer

## Slide 6
Member States Approve S-101
Update S-57 to S-101 Convertor
Finalize S-101
User Review and Input
OEMs Implement S-100 based ECDIS
ECDIS On-Shore Trials
Converted S-57 or Full S-101 ENC Data Available
S-101 Test Bed Development and Iterative Testing
ECDIS Sea Trials
OEMs Develop S-100 ECDIS
HSSC Approves S-101
S-101 Draft Version
IEC 61174 PAS made available
Draft S-58 & S-64 for S-101 Available
Complete Portrayal Section of S-100
Finalize Portrayal Section of S-101
Finalize Draft of S-101 for Testbed
Update S-57 to S-101 Convertor and Make Sample S-101 Data Available for Review
Sample S-101 Data made Available
Retire S-57 and S-52
Contract to Create Portrayal Catalogue Builder
Final S-101 Stakeholder Review
OEMs
TSMAD
HOs
Stakeholders
DIPWG
Responsible Party
S-101 Development and S-100 Testbed Timeline
Draft S-58 & S-64 for S-101
Release S-101 for Operational Use
S-101 Test Bed Development and Iterative Testing
Draft S-58 and S-64 for S-101
User Review and Input
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC
JAN
FEB
MAR
2013
2014
2014
2015
2016
2017
2019
2018
2013
…
Prepare Test Data – Feature and Portrayal Catalogues and test datasets

## Slide 7
PRODUCERS
S-101 Data Exported
RENCs
S-100 ECDIS
S-101 SENC
S-57 SENC
S-57 ECDIS
Package S-57 Data
S-101 Converted
S-101 Converted
VARs
Package S-57 Data
S-101 Converted
S-101 Converted
S-57 Data Exported
Package S-101 Data (converted and native)
Package S-101 Data (converted and native)