## Slide 1: Progress Report on the Establishment of EA-RECC
Hydrographic Office,
Marine Department
Hong Kong SAR Government
China
The 8th IHO WENDWG
20 - 22 March 2018, Buenos Aires, Argentina

## Slide 2: Establishment of EA-RECC
Background
Upon the endorsement given in the last SC meeting in Feb 2017, Hong Kong China had subsequently started the preparatory work for the establishment of EA-RECC in March 2017;
As of March 2018, the key preparatory work included:
  Staff recruitment and training
  Setting up of office area
  Drafting TOR, ROP and Operating Guidelines
  Contacting with other RENCs

## Slide 3: Staff Recruitment
Q2 2017
Clerical Assistant
Q2 2018

## Slide 4: Staff Recruitment
Group Photo
The team of the EA RECC

## Slide 5: Staff Training
SevenCs ENC Tools Training (Feb 2018)
  IHO Standards (S-57, S-58 and ENC Data Production)
  Introduction to ENC Designer
  Introduction to ENC Referencer
  Introduction to ENC Manager
  Introduction to ENC Optimizer
  ENC Validation using ENC Analyzer
  Source Data Conversion ( focus on FME S-57 Writer)
  Introduction to S-100 and latest development

## Slide 6: Staff Training
SevenCs ENC Tools Training

## Slide 7: Staff Training
EAHC Cat C Charting Training
  Conducted by the centre’s Chief Geodata Officer who is a qualified trainer;
  EAHC 1.0 Chart Data Assessment
  EAHC 1.1 Verification Process and Data Assessment
  EAHC 2.0 Paper Chart Compilation
  EAHC 3.0 Basic ENC Production
  EAHC 3.1 Introduction to ENC
  EAHC 3.2 ENC Production
  EAHC 4.0 Preparation of chart updating
  EAHC 4.1 Notice to Mariners
  EAHC 4.2 Chart Maintenance

## Slide 8: Staff Training
EAHC Cat C Charting Training

## Slide 9: Setting up of office area
The EA-RECC is located in the Hydrographic Office of Hong Kong
Setting up of office area:
  By conversion of an existing conference room and some other ancillary area into office area;
  Fitting out works and furnishing;
  Procurement of Hardware and Software
  The works started in August and completed in December 2017;

## Slide 10: Setting up of office area
Vacated conference room ready for conversion

## Slide 11: Setting up of office area
Building Works in Progress

## Slide 12: Setting up of office area
Building Works in Progress

## Slide 13: Setting up of office area
The new office area for the EA RECC

## Slide 14: Setting up of office area

## Slide 15: Contact with Other RENCs IC-ENC
Attended the 2nd IC-ENC Technical Conference as observer, 22 –24 May 2017, Copenhagen, Denmark
Key areas observed:
  Latest development in IC-ENC
  Validation Overview
  Errors Database update
  ENC Validation Training Overview
  Data Management Tools
  Quality Assurance Issues
  Commercial products presentations

## Slide 16: Contact with Other RENCs IC-ENC
Attending (as observer) IC-ENC Technical Conference, TC02, 22 –24 May 2017, Copenhagen, Denmark

## Slide 17: Contact with Other RENCs IC-ENC
Workshop on the Implementation and Operation of a Regional ENC Coordination Centre
Conducted in HKHO in July 2017 with guest speaker Mr. James Harper, IC-ENC General Manager;
Attended by the key EA-RECC project staff;
This workshop provided a two-way flow of information:
  The EA-RECC goals, purpose, project plan etc,
  The IC-ENC global operating model of four core services (production support, validation, distribution and revenue management), financial model and governance.

## Slide 18: Contact with Other RENCs IC-ENC
Workshop on the Implementation and Operation
of a Regional ENC Coordination Centre

## Slide 19: Contact with Other RENCs IC-ENC
Meeting with Mr. James Harper, General Manager of IC-ENC

## Slide 20: Contact with other RENCs PRIMAR
Attended the PRIMAR 15th Technical Expert Working Group Meeting as observer, 28-29 November 2017, Stavanger, Norway
Key areas observed:
  Latest development in PRIMAR
  RENC-RENC cooperation
  Technical issues – S-101, S-102 & S-58
  PRIMAR’s Errors Database
  T&P Notices
  Chart Catalogue on WEB
  Commercial products presentations

## Slide 21: Contact with other RENCs PRIMAR
Visiting PRIMAR office and meeting with their management staff;
Key issues discussed:
  Organisation, status and operations of PRIMAR as a RENC;
  Technology and tools applied in daily operations;
  Opportunities for RENC-RENC cooperation

## Slide 22: Contact with other RENCs PRIMAR
Visiting PRIMAR office, Stavanger, Norway

## Slide 23: Drafting TOR, ROP and other documents for EA-RECC
TOR and ROP for the Board of Directors of EA-RECC;
TOR and ROP for EA-RECC;
Administrative procedures;
Procedure for handling of data flow and sales records;
Staff training plan

## Slide 24
- Thank You -
Progress Report on the Establishment of EA-RECC