## Slide 1: 16th MACHC Conference
Agenda item 1.5
MACHC Action list Review

## Slide 2
Procedure for dealing with action list (1)
Open actions
Proposal in column status.
Focus on concrete deliverables, so when deliverables are unclear or actions are overtaken by events, close them.
Not within the remit of TOR, close them.
Continuous actions.
If already standing activities/responsibilities within the MACHC structure, than review no longer and close.
Remainder in separate list for future reference as they do not have a specific deliverable in time.
Completed or closed actions.
Stop reporting them on an action list.

## Slide 3
Procedure for dealing with action list (2)
Chair requested participants of the MACHC to study this procedure and these proposals beforehand with the aim to save a lot of processing time.
Now concentrate on the more important issues. In presentation potential candidates are selected and highlighted.

## Slide 4
Action item | Subject mater | Agreement | Responsible party | Due date | Status
List of actions 15th MACHC meeting |  |  |  |  | 
15.5.2.2 | IRCC | Follow up on MACHC paper regarding Maximizing the use of survey data | Chair MACHC | XVIth MACHC meeting | Rewrite. MS encouraged to act in line with IRRC 7 papers 11B/11E in anticipation of IRRC7 action 67
15.6.2.3 | National report | Technical visit to Haiti postponed to 2016 because of busy political agenda in Haiti. | CB Coordinator, IHB and Chair MACHC | 2016 | Rewrite. High level technical visit as CBWP funded has been superseded by a technical visit by US Authorities.
15.6.2.4 | National report | IALA to assist Haiti in preparing for the technical visit. | IALA and Haiti | XVIth MACHC meeting | Unknown, TBC by IALA
15.6.2.6 | National report | ESRI will try to make its data available to Haiti. | ESRI | XVIth MACHC meeting. | Unknown, TBC by ESRI
15.6.2.9 | National report | Venezuela to make their hydrographic products available to the MACHC. | Venezuela | XVIth MACHC meeting. | Unknown, TBD at meeting (MICC Chair?)
15.6.2.11 | National report | Spain to assist Mexico and other MACHC countries with the language issue (resolve the issue regarding courses) [or resources??]. | Spain | XVIth MACHC meeting. | Constant, bilateral activity.
Open action items (1)

## Slide 5
Action item | Subject mater | Agreement | Responsible party | Due date | Status
List of actions 14th MACHC meeting |  |  |  |  | 
14.1.13 | 7 | CB Coordinator to put together a questionnaire to assess how students use the training in their work. | CB Coordinator | 15 may 2014 | Close. No specific MACHC proposal at CBSC13 as this is a wider issue and a perpetual challenge for the IHO’s CB activities (how success is measured).
14.1.25 | 12 | Chair will send a letter to the IHB with regard to the link between Hydrography and Oceanology | MACHC Chair | March 2014 | Rewrite, all are invited to provide their assessment on the underlying problem and how this effects the Link.
Open action items (2)

## Slide 6
Action item | Subject mater | Agreement | Responsible party | Due date | Status
List of actions 13th MACHC meeting |  |  |  |  | 
14.3.6 (13.3.6) | CB | Gulf of Fonseca project: Decision to continue the project discussions with authorities from the three Member states. Recognize that the future development of the Gulf of Fonseca can benefit from the works proposed by this project; including hydrography for the safety of navigation, physical oceanography for the protection of the marine environment, and coastal zone management. Decision to keep this project Regional within Central America as much as possible | PAIGH, Honduras, Nicaragua, El Salvador, | Undetermined | Ongoing, back brief required at meeting. Question: Bilateral or MACHC/CB project?
14.3.7 (13.3.7) | CB | Investigate the feasibility of Spanish online training similar to that of the Hydrographic Academy of University of Plymouth. | CB Coordinator | MACHC14 meeting | Close, not feasible within restraints of CBWP (funding). Online training potentially part of FOCAHIMECA project or action 15.6.2.11
List of Actions 12th MACHC meeting |  |  |  |  | 
Open action items (3)

## Slide 7
Continuous action items
Action item | Subject mater | Agreement | Responsible party | Due date | Status
List of actions 15th MACHC meeting |  |  |  |  | 
List of actions 14th MACHC meeting |  |  |  |  | 
List of actions 13th MACHC meeting |  |  |  |  | 
14.1.42 (13.1.10) | MACHC 13 | MACHC Member States to include 'sharing experience in dealing with maritime disasters’ as a standing MACHC agenda item | MACHC Chair | Continuous action (By 14th MACHC meeting) | Ongoing, as agenda item every MACH meeting
List of Actions 12th MACHC meeting |  |  |  |  |