Proposed revision of the Draft IHO Marine Spatial Data Infrastructure Working Group (MSDIWG) Work Plan

MSDIWG WORK PLAN 2015–20

MSDIWG Tasks

| A | Identify and promote national and regional best practices |
| --- | --- |
| B | Assess the existing and new standards in the provision of marine components of spatial data infrastructures |
| C | MSDI training and education |
| D | Facilitate (external) MSDI communication |
| E | Maintain and extend the publication IHO MSDI C-17 (IHO Task 2.9.2 refers) |
| F | Conduct annual meetings of MSDIWG, arranged back to back with 1-day MSDI Open Forum (IHO Task 2.9.1 refers) |
| G | Ensure that MSDI is a standing agenda item for RHCs’ meetings (IHO Res 2/1997, as amended, refers) |

| No | Work item | Priority H-high M-med L-low | Milestones | Start Date | End Date | Status P-planned O-ongoing C-completed | Responsible / contact person(s) | Related Pubs / Standard | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A.1 | Set up a survey to establish current position in respect of benefits and challenges faced by MS’s role in NSDI and/ or MSDI | H | Prepare questionnaire Review status of MS Analyse/report results MS report to each MSDIWG annual meeting listing successes and challenges and ways of overcoming them | Feb 2015 | Jun 2016 | P | Canada MS |  |  |
| A.2 | Monitor and report on national, regional and international MSDI activities and report to enable increased visibility of hydrographic importance | M | Engage with relevant initiatives Report level of MS involvement | Apr 2014 | Jan 2019 | O |  |  | Report to MSDIWG-6. |
| A.3 | MS to identify relevant use cases for MSDI and report to MSDIWG | H | Create the foundation for MSDI business cases/case studies Create relevant use cases, from potential users of MSDI | Feb 2016 | Jun 2018 | P | GSDI |  |  |
| B.1 | Identify HO datasets and use cases for the use in MSDI | H | Create/develop and maintain relevant MSDI matrixes INSPIRE | Feb 2015 | Jan 2018 | O | Ocean |  |  |
| B.2 | Review standards and specifications relevant for MSDI | M | Determine and log any issues of concern in WG regarding existing and new standards (S-57, S100, INSPIRE, UN-GGIM, ISO and OGC) Seek clarification on any concerns in S-1XX development as seen from a MSDI perspective |  |  |  | Netherlands |  |  |
| B. 3 | Provide annual technical reports to HSSC through IRCC if needed | H |  |  |  |  | Chair |  |  |
| C.1 | Establish and maintain a MSDI training syllabus for use across IHO community | H | Establish syllabuses for 3 MSDI courses and a MSDI orientation For Senior Managers (i.e. Directors, Hydrographers, HR Managers) Practitioners (i.e. Hydrographic Surveyors, Cartographers, Oceanographers, IT specialists) | Jan 2014 | Jan 2018 | O | Chair & Secretary. |  |  |
| C.2 | E-learning | H | Request CBSC through IRCC to facilitate e-learning for MSDI | Feb 2016 | Jan 2018 | P | Chair/sec |  |  |
| C.3 | Outreach to academia and other bodies to promote and contribute to MSDI in the hydrographic community | M | Investigate the possibilities for establish a MSDI work shop wider audience | Feb 2016 | Feb 2019 | P | Chair/sec |  |  |
| D.1 | Update the IHO MSDI webpage | M | Maintain MSDI reference documentation on the IHO website Identify and make available MS Web sites/papers that address technical issues such as datum, WMS, WFS for charting data. Poll MSDIWG members for input work, with IHB to post on IHO Web site. Investigate the possibility for an additional new web address for the MSDI webpage | Oct 2013 | 2018 |  | IHB |  |  |
| D.2 | MSDI communication and dissemination |  | Support the establishment of a Linked in MSDI group Creation of a MSDI “white” paper |  |  |  | CARIS |  |  |
| D.3 |  |  |  |  |  |  |  |  |  |
| E.1 | Update the publication IHO MSDI C-17 | H | Update information Provide case studies Best practice guidelines defined | Feb 2015 | Oct 2019 | P |  | C 17 C-17/CBSC MSDI Syllabus, INSPIRE, OGC, ISO, IHO, RHC reports, MSDIWG MS inputs |  |
| E.2 | Presentation of C-17 | H | Investigate new options with IHB of presenting C-17 as a web publication |  |  |  |  |  |  |
| F.1 | Conduct 2016 meeting of MSDIWG, arranged back to back with 1-day MSDI Open Forum | H | 3-day workshop to be run Q1 of each year; 2016 Japan | Feb 2015 | Feb 2016 | o | MSDIWG Management Group (Chair/Vice Chair, Sec, IHB rep); representative |  |  |
| F.2 | Conduct 2017 -20 meetings of MSDIWG, arranged back to back with 1-day MSDI Open Forum | M | Date and venue defined Logistics in place Conference programme defined Develop Workshop programmes | Sep 2013 | Jan 2018 | P | MSDIWG Management Group (Chair/Vice Chair, Sec, IHB rep) |  |  |
| G.1 | Ensure that MSDI is a standing agenda item for RHCs’ meetings (IHO Res 2/1997 as amended) | H | MSDIWG paper to IRCC re-stating importance of RHC’s placing MSDI as an agenda item at RHC meetings. MSDI inputs and actions from RHC’s fed back to MSDIWG Ensure that MSDI is a standing agenda item for RHCs’ meetings and RHCs’ report back to MSDIWG: Investigate new options: Should the MSDIWG appoint MSDI ambassadors in RHC? Should the MSDIWG provide standard MSDI presentations to RHC? Should the MSDIWG establish best practise MSDI cases for RHC? | July 2015 | June 2016 | O | MSDIWG Chair/Vice Chair | HSSC, IRCC, CBSC |  |

MSDIWG Meetings (Task F)

| Date | Location | Activity |
| --- | --- | --- |
| 2-3 Apr 2009 | IHB, Monaco | MSDIWG 3 |
| 8 & 13 Sep 2011 |  | Conference Calls |
| 30 Jan – 01 Feb 2013 | Copenhagen, Denmark | MSDI Open Forum + MSDIWG 4 |
| 4-7 Feb 2014 | Silver Spring, Ma, USA | MSDI Open Forum + MSDIWG 5 |
| 2015 |  |  |

Chair: Jens Peter Hartmann, Denmark		Email: jepha@kms.dk

Vice-chair: Ellen Vos, Netherlands			Email: em.vos@mindef.nl

Secretary: John Pepper, OceanWise	  	Email: john.pepper@oceanwise.eu