**LIST OF ACTIONS FROM HSSC-7**

| **SUBJECT** | **ACTION****No.** | **ACTIONS****(in bold, action by)** | **TARGET****DATE/EVENT** | **STATUS****(at 8 Feb 2016)** |
| --- | --- | --- | --- | --- |
| Contact List | HSSC7/01 | **IHO Member States** to provide the IHB with their updates to the HSSC List of Contacts. | **Permanent** |  |
| HSSC Programme Performance Indicators (PIs)  | HSSC7/04 | Inputs to the current HSSC WPI for the 2014 period to be provided by **HSSC WG Chairs** (Performance Indicators No 2 and 3) and **WEND WG Chair** (Performance Indicator No 5) by 31 January 2016. | **31 Jan. 2016** | Completed, delivered by due date |
| IHO Strategic Plan - IHO 3-year Programme of Work | HSSC7/05 | **Chairs of HSSC WGs** to collect the views of their members on the IHO Strategic Plan and the IHO 3-year Programme of Work | **By end of April 2016** | Planned |
| S-100 Domains | HSSC7/07 | **NIPWG** to submit to the **S-100WG** a proposal relating to harmonization requirements within the different domains of the Feature Concept Dictionaries. | **February 2016** | Completed, paper forwarded to the S-100WG for consideration |
| S-1xx Portrayal Issues | HSSC7/19 | **NIPWG** to experiment a workflow with stakeholders (industry, academia, …) and other HSSC WGs (S-100WG, DQWG, …) for S-122 portrayal issues. | **HSSC-8** | Planned |
| S-122 test beds | HSSC7/20 | For S-122, and assuming that sufficient information is available, **NIPWG,** in liaison with NCWG and S-100WG, to make use of test beds opportunities (e-navigation projects as appropriate). | **HSSC-8** | Planned |
| Harmonized display of navigation information | HSSC7/35 | **NIPWG** to coordinate the contribution of the IHO to the development of guidelines for the harmonized display of navigation information and to the preparation of the output related to the development and implementation of maritime service portfolios (MSPs), notably in liaison with the WWNWS-SC. | **HSSC-8** | paper on harmonised display was discussed see HSSC7/36, MSP is under discussion |
| Harmonized display of navigation information | HSSC7/36 | **S-100WG** to prepare, in liaison with **NIPWG**, the **IHB** and the **HSSC Chair**, a submission on the contribution of the S-100 framework to the harmonized display of navigation information and the impact on existing performance standards for consideration by NCSR 2 (deadline: 25 Dec 2015). | **18 Dec. 2015** | completed |
| Polar Code | HSSC7/40 | **NIPWG and NCWG** to consider improvements to current IHO specifications or other actions which could facilitate the implementation of the provisions of the Polar Code related to charting issues (Part I-B, Additional Guidance to Chapter 9 (Safety of Navigation) refers). | **HSSC-8** | Planned |
| Unique Identifiers | HSSC7/41 | **NIPWG and S-100WG** to consider referring the issue of Unique Identifiers to the IMO-IHO Harmonization Group on Data Modelling and report to HSSC-8 (see Action HSSC7/42). | **HSSC-8** | completed, paper forwarded to the S-100WG for consideration |