**Annex A: List of Actions:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Planned tasks for this Reporting Period** | | | | |
| Action Item | Actor | Task Description | Target End Date | Task Status  As per 4 Januar |
| XML1 | All | Check the completeness of the various enumeration values | 31 October 2018 | completed |
| XML2 | DE | A simplified DCEG will be developed which describes only UML components in details which are not bijective | 31 December 2018 | completed |
| XML3 | DE (Jens) | Finding a common repository and exchange mechanism for XML based corrections which should be hosted by the Secretariat. Each HO can deliver and receive the XML automatically | 31 December 2018 | In progress |
| XML4 | DE (Jens( | Draft a response paper to WWNWS-CG, distribute between participants for comments before submission | 15 November 2018 | Completed, bespoken at IALA ARM meeting Oct. 2018 |
| XML4 | FI (Stefan) | Preparing an input paper for NIPWG6 | January 2019 |  |
| XML5 | All | Each participating HO produces 10 different examples of NtM chart corrections which should be converted from their own XML to the common XML | 31 January 2019 |  |
| XML6 | IT (Ludovico) | Test to put the common XML information into CARIS publication module using Italian NtM structure as an output | 28 February 2019 |  |
| XML7 | DE (Daniel) | Test to put the common XML information into CARIS publication module using German NtM structure as an output. | 28 February 2019 |  |
| XML8 | DE (Daniel) | Develop an XSLT to provide an HTML output of the examples | 28 February 2019 |  |
| XML9 | FI (Stefan) | Develop a translation from the common XML format to RSS | tentatively, if time allows, potentially by 31 March 2019 |  |
| XML10 | NO (Rade) | Test to put the common XML information into the Norwegian system and produce an output according the No NtM | 31 March 2019 |  |
| XML11 | ROK (Yong) | Test the common XML to generate an output in Korean/English language according to the Korean NtM style | 31 March 2019 |  |
| XML12 | DE (Jens) | Contact IHO Sec to find an appropriate place for providing the workshop output. That includes “best practice” XML for exchanging HO NtM data. | 31 December 2018 |  |
| XML13 | DE (Jens) | Initiate a follow-up workshop in September 2019 (exchange of experience, improve data model, consider additional requests)  Contact NIPWG6  Apply HSSC endorsement (noting that we reflect the outcome of the testing base) |  |  |